## Sprint NN Backlog
Sprint #	Final Sprint
Start on	04/10/17 12:00 AM
End on	04/18/17 07:00 AM
Demo on	05/02/17 12:00 AM

Total Tasks	31
Day 1 Left	28
Day 2 Left	26
Day 3 Left	20
Day 4 Left	12
Day 5 Left	7
Day 6 Left	3
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	Create_Robot_Parts	Architecture	UML	NK	Create a use case diagram	CO	Use case diagram is subject to change depending on the features being added
2	Create_Robot_Parts	Architecture	UML	NK	Design a relation between classes	CO
3	Create_Robot_Parts	Architecture	UML	Nk	Add data types and methods to Robot_parts	CO
4	Create_Robot_Parts	Architecture	code	NK	Add data types and methods to Robot_model and design main	CO
5	Create_Robot_Parts	Robot_Parts	code	NK	establish relation with derived classes and compile	CO
6	Create_Robot_Parts	Robot_Parts	debug	NK	fix declaration	CO
7	Create_Robot_Parts	Robot_Parts	code	NK	Add power field and getters	CO
8	Create_Robot_Parts	Robot_Parts	code	NK	Compile Code	CO
9	Create_Robot_Parts	Robot_Parts	Test	NK	Use regression to verify getters	CO
10	Create_Robot_Parts	Robot_Parts	code	NK	Compile Code	CO
11	Create_Robot_Parts	Head	code	NK	Create head class with methods	CO
12	Create_Robot_Parts	Arm	Test	NK	Create arm class with methods	CO	max_power is used by Head and Arm
13	Create_Robot_Parts	Head	code	NK	use regression test to test the classes	CO
14	Create_Robot_Parts	Locomotor	code	NK	Create Locomotor class with methods	CO
15	Create_Robot_Parts	Locomotor	descion	NK	Decide how to respond yo invalid inputs	CO
16	Create_Robot_Parts	Torso	code	NK	Create Torso class with methods	CO
17	Create_Robot_Parts	Battery	code	NK	Create battery class with methods	CO
18	Create_Robot_Parts	Torso	Test	NK	use regression test to test the classes	CO
19	Create_Robot_Parts	Battery	Debug	NK	corrected inheritance bug	CO
20	Create_Robot_Parts	Battery	UML	NK	confirm the UML is up to date	CO
21	create Robot model	Architecture	UML	NK	Design a relationship between Robot Parts and Robot Models	CO	Makes implementation of Robot_models possible
22	create Robot model	Architecture	UML	NK	Design a relation between classes	CO
23	create Robot model	Architecture	UML	NK	Add Methods to Robot_model and implement relations with Robot_part	CO
24	create Robot model	Create_Robot_model	code	NK	Use data to implement Robot_model_methods	CO
25	create Robot model	Create_Robot_model	debug	NK	fixed inheritance problem with robot_parts	CO
26	create Robot model	Create_Robot_model	code	NK	compile code	CO
27	create Robot model	Create_Robot_model	code	NK	created another vector for storing string	CO
28	create Robot model	Create_Robot_model	debug	NK	fix pointer bug	CO
29	create Robot model	Create_Robot_model	code	NK	use vectors to store robot models	CO
30	create Robot model	Menu Selection	code	NK	Design menu to provide user options	CO
31	create Robot model	Menu Selection	code	NK	handling user input gracefully	CO
32	create Robot model	Menu Selection	debug	NK	corrected exceptional case of user input	CO
33	create Robot model	Create_Robot_model	code	NK	compile code	CO
34	create Robot model	Create_Robot_model	code	NK	created another vector for storing string	CO
35	create Robot model	Create_Robot_model	debug	NK	fix pointer bug	CO
36	create Robot model	Create_Robot_model	code	NK	use vectors to store robot models	CO
37	create Robot model	Menu Selection	code	NK	Design menu to provide user options	CO
38	create Robot model	Menu Selection	code	NK	handling user input gracefully	CO
39	create Robot model	Menu Selection	debug	NK	corrected exceptional case of user input	CO
40	create Robot model	Menu Selection	GUI	NK	Design GUI	CO
41	create user type	Menu Selection	GUI	NK	Design GUI	CO
42	GUI Dialogs	Robot_Parts	GUI	NK	Design GUI	CO
43	Define Robot Models	Robot_Models	GUI	NK	Associated it with Beloved customer and Sales associate	CO	This is to keep track of who is buying our products
44	Display Robot Models	Shop	GUI	NK	Browse catalog for robots	CO
45	GUI Implementation	Robot_Models	code	NK	compile code	CO
46	GUI Implementation	Robot_Models	debug	NK	fix compilation error	CO
47	GUI Implementation	Wrap_Up	Delivery	NK	create a zip folder and deliver	CO
Sprint Burn Chart
Tasks
Days