## Sprint NN Backlog
Sprint #	4				*** Example Only – Set up a tab for EACH SPRINT ***
Start on	04/20/17 12:00 AM
End on	05/02/17 07:00 AM
Demo on	05/02/17 12:00 AM

Total Tasks	31
Day 1 Left	28
Day 2 Left	26
Day 3 Left	20
Day 4 Left	12
Day 5 Left	7
Day 6 Left	3
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	create Robot model	Create_Robot_model	code	NK	compile code	CO
2	create Robot model	Create_Robot_model	code	NK	created another vector for storing string	CO
3	create Robot model	Create_Robot_model	debug	NK	fix pointer bug	CO
4	create Robot model	Create_Robot_model	code	NK	use vectors to store robot models	CO
5	create Robot model	Menu Selection	code	NK	Design menu to provide user options	CO	browse a catalog of robot models
6	create Robot model	Menu Selection	code	NK	handling user input gracefully	CO
7	create Robot model	Menu Selection	debug	NK	corrected exceptional case of user input	CO
8	create Robot model	Menu Selection	GUI	NK	Design GUI	CO
9	create user type	Menu Selection	GUI	NK	Design GUI	CO
10	GUI Dialogs	Robot_Parts	GUI	NK	Design GUI	CO
11	Define Robot Models	Robot_Models	GUI	NK	Associated it with Beloved customer	CO
12	Display Robot Models	Shop	GUI	NK	Browse catalog for robots	CO	browse catalog of robots via a GUI report
13	GUI Implementation	Robot_Models	code	NK	compile code	CO
14	GUI Implementation	Robot_Models	debug	NK	fix compilation error	CO
Sprint Burn Chart
Tasks
Days