## Product Backlog
Product Name:	KebeRobotics					Fields in blue expect your input!
Team ID:	Natnael Kebede

Name:	Natnael Kebede
Initials:	NK
Student ID:	1001149004

(Additional names for teams only)
Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Total Features	Left	Available	Completed	Sprint Ends
Total at Start	32	32
Sprint 1	32	32	1	Mar 28
Sprint 2	31	32	1	Apr 04
Sprint 3	31	32	1	Apr 11
Sprint 4	31	32	1	Apr 18
Sprint 5	31	32	1	Apr 25
Sprint 6	31	32	1	May 02

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Sprint # (by team size)					Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Prio	Status	Actual Sprint #	1	2	3	4	Pts	Cml	As a...	I want to...	So that...	Type	Notes
Create Robot_parts	1	CO	1	1	1	1	1	21	21	PM	create robot parts	I can define robot models	CLI	No menu required here – run program, create a part
Create Robot_Models	2	CO	2	2	1	1	1	13	34	PM	define new robot models	RRS can sell them to our Beloved Customers	CLI	Menu needed – create parts, then create a robot model
Create_BC	3	CO	2	2	1	1	1	5	39	BC	browse a catalog of robot models	I can buy one or more robots	CLI	Need to list robots models, then list parts in selected model
Create_BC	4	CO	3	3	2	1	1	3	42	PB	create a new Beloved Customer	I can keep track of who's buying our products	CLI	The usual name, customer number, phone number, and email address
Create_SA	5	CO	3	3	2	1	1	3	45	PB	create a new Sales Associate	I can keep track of my employees' performance	CLI	Name and employee number at a minimum
SA_Order	6	CO	3	3	2	2	1	8	53	SA	create a robot order for a Customer	I can sell robots and thus do my job well	CLI	Select robot model and quantity, show details with total price
Save_Default	7	CO	3	3	2	2	2	13	66	PB	ensure persistence of the RRS data	we don't lose orders or historical data	CLI	(CLI) Write the data to the default filename and reload it next time the program runs
GUI_Main	8	CO	4	4	3	2	2	3	69	All	open a GUI main window	I can interact with RRS Manager with my mouse	GUI	No menu required here – run program, create a part
GUI_CP	9	CO	4	4	3	2	2	34	103	PM	create robot parts via GUI dialogs	I can define robot models	GUI	An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
GUI_CM	10	CO	5	5	4	3	3	21	124	PM	define new robot models via GUI dialogs	RRS can sell them to our Beloved Customers	GUI	Similar to robot parts (perhaps Create > Robot Model)
GUI_Browse	11	NS	6	6	4	3	3	8	132	BC	browse a catalog of robots via a GUI report	I can buy one or more robots	GUI	A text output is OK initially, but an attractive HTML-like output is desired (perhaps Report > All Robot Models)
GUI_SA_Order	12	NS			5	4	3	21	153	SA	create a robot order for a Customer via GUI	I can sell robots and thus do my job well	GUI	As with CLI (and you’ll need the CLI to add BC and SA people)
GUI_Manage	13	NS			5	4	4	13	166	PB	manage a robot order for a Customer via GUI	I can ensure the robot is built and ships	GUI	This will involve a state machine implementation
GUI_Create_Browse	14	NS			5	4	4	8	174	PB	create a new Beloved Customer via GUI	I can keep track of who's buying our products	GUI	The usual name, address, phone number, and email address (perhaps Create > Customer)
GUI_Create_SA	15	NS			5	4	4	5	179	PB	create a new Sales Associate via GUI	I can keep track of my employees' performance	GUI	Name and employee number at a minimum (perhaps Create > Sales Associate)
Robot Pictures	16	NS			6	5	4	13	192	BC	see pictures of the robots in the GUI catalog	I can see what I'm buying	GUI	Add picture when defining robot model, and show it in the robot model report
	17	NS			6	5	4	5	197	PB	allow the users to save data explicitly via GUI	we can save data without exiting the program	GUI	Write the data to the default filename on command (perhaps File > Save to the default filename)
	18	NS			6	5	4	8	205	PB	allow the users to load data explicitly via GUI	we can manage multiple stores in different files	GUI	Read the data from a user-selected file on command (perhaps File > Open)
	19	NS			6	5	4	8	213	PB	allow the users to save data to a specified name via GUI	we can manage multiple stores in different files	GUI	Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
	20	NS				5	5	13	226	PB / SA	view a report of orders per SA in the GUI	I can estimate the value of employees / / I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	21	NS				6	5	21	247	All	enable basic login by role and customize the GUI	we don't have options that don't apply to our roles	GUI	User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
	22	NS				6	5	13	260	All	enable copy and paste from text fields	we can save typing	GUI	Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported
	23	NS				6	6	13	273	BC	view my bill (invoice) in the GUI	I can pay for my robots	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
	24	NS					6	8	281	BC	view my orders in the GUI	see what I have coming to me	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
	25	NS					6	8	289	SA	view a sales report in the GUI	I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	26	NS					6	8	297	PB	view a report of all orders in the GUI	I can manage the company	GUI	A basic text report is fine (perhaps Report > All Orders)
	27	NS					6	13	310	All	Add multi-level undo	Worry less about making mistakes	GUI	This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
	28	NS					21	331	BC	see a pie chart of a model's component costs	I can decide if I want a different model	GUI	Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
	29	NS					13	344	SA	create a bulk (2+) order for Customer via GUI	avoid proliferation of orders and paperwork	GUI	Allow more than one robot model (with respective quantity) on a single order
	30	NS					8	352	PM	hide robot parts via GUI	obsolete parts aren't accidentally used	GUI	Mark robot parts as “obsolete” and don't allow adding them to new robot models
	31	NS					8	360	PM	hide robot models via GUI	obsolete robots aren't ordered	GUI	Mark robot models as “obsolete” and don't allow adding them to new orders
	32	NS					21	381	SA	save a draft order and return to it later via GUI	I can multi-task between indecisive customers	GUI	Save an order that hasn't been complete, and allow SA to resume work on it later
Product Backlog Burn Chart
Sprints
Features Remaining at Start of Sprint

## Sprint NN Backlog
Sprint #					*** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on

Total Tasks	0
Day 1 Left	0
Day 2 Left	0
Day 3 Left	0
Day 4 Left	0
Day 5 Left	0
Day 6 Left	0
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
Sprint Burn Chart
Tasks
Days